ICMR-STS Workflow

Done over 3 years in summer vacation time, first 2 months is preparation of Concept Note and its submission, second 2 months is Data collection, third 2 months is Data analysis, Preparation and submission of Report. (Please refer to ICMR-STS website for most recent information and in case of  change in formats)

1. Notification Release – Details of the scheme are announced.

2. Idea/Department Selection – Identify a research topic.

3. Approach Guide – Consult a guide.

4. Finalize Research Topic – Confirm with guide.

5. Concept Note/Proposal Preparation – Conduct literature search.

6. Register & Submit Proposal to ICMR

Submit with Letter of Approval from Dean (Research) and signature of Department Head.

7. ICMR Selection

If selected, the first instalment ₹15000 is received at the end of the first year.

8. Submit Proposal to UGRMC via Email (PDF Format)

No UGRMC meeting required.

UGRMC certificate issued.

9. Submit Proposal to IEC (Soft & Hard Copies)

10. IEC Meeting – Attendance mandatory for PI & Guide.

11. Proposal Modifications – Changes suggested & sent via email within 1-2 weeks.

12. Resubmit Modified Proposal to IEC

13. IEC Certificate Issuance – Project can commence.

14. Second-Year Summer Vacation: Data Collection

15. Submit Interim Report to ICMR

Second instalment ₹15000 received at the end of the second year.

16. Third-Year Summer Vacation: Data Analysis

Assistance from Guide/PSM Resident/Biostatistics Faculty.

17. Final Report Preparation & Submission to ICMR

18. Final Instalment ₹30000 & ICMR-STS Certificate Issued

---

Document Submission Requirements

For IEC meeting

Soft Copy: (Both PDFs & Word Documents)

Signed Declaration Form

Consent/Waiver of Consent Form

Proposal

Covering Letter

Hard Copy:

Covering Letter

Consent/Waiver of Consent Forms

Research Proposal with Signed Declaration Form

Data Collection Proformas

CV of PI, Guide, & Co-Guides

GCP certificate ( for interventional studies)